## Control Sheet
Scenario Id | Sub Scenario Id | Description | Expected Result | Assigned To | Reviewed by | Weekday - 1 | [6 empty] | Weekday - 2 | [6 empty] | Weekday - 3 | [6 empty] | Weekday - 4 | [6 empty] | Start Date | End Date
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 |  | Authentication |  | Aiswarya | Rajesh S | [28 empty] | 13/6/2014 | 14/6/2014 | bar: Weekday - 2 5 to Weekday - 2 6
| 1.1 | Authentication | User Should get Authenticated
| 1.1.1 | User Registration | New User Should get Registered
| 1.1.2 | User Sign In | User Should be allowed to Login
2 |  | Home |  | Aiswarya | Rajesh S | [28 empty] | 14/6/2014 | 14/6/2014 | bar: Weekday - 2 6
| 2.1 |  | User Should Navigate to Mobile Phones Page | Aiswarya
| 2.2 |  | User should be Provided with 2 category | Aiswarya
| 2.2.1 |  | User should be provided with Choices | Aiswarya
| 2.2.2 |  | User should be provided with Choices | Aiswarya
3 |  | My Books |  | Aiswarya | Rajesh S | bar: Weekday - 2 5 to Weekday - 2 6
| 3.1 |  | Samsung option should provide Refine Options | Aiswarya
4 |  | Browse |  | Aiswarya | Rajesh S
5 |  | Community |  | Aiswarya | Rajesh S

## Test Scenario
Scenario Id | Sub Scenario Id | Description | Expected Result
1 |  | Authentication
| 1.1 | Sign Up | User should get registered
| 1.2 | Sign In | User should be allowed to login
| 1.2.1 | With email address and password | User should be able to login with registered email address and password
| 1.2.2 | Using Facebook account | User should be able to login with a valid Facebook account
| 1.2.3 | Using Twitter account | User should be able to login with a valid Twitter account
| 1.2.4 | Using Google account | User should be able to login with a valid Google account
| 1.2.5 | Using Amazon account | User should be able to login with a valid Amazon account
2 |  | Home
| 2.1 | Currently Reading | User should be able to search for boks, get recommendations and post upates
| 2.1.1 | Search Books | User should be able to search for books and get suggestions as the name is typed
| 2.1.2 | Recommendations | User should get suggestions on what books to read based on their reading taste
| 2.1.3 | General Update | User should be able to update their status on books and reading schedules
| 2.2 | Reading Challenge | User should be able to set target number of books for the current year
| 2.2.1 | Set challenge | User should be able set the number of books he intend to finish reading during the current year
| 2.3 | Friends on goodreads | User should be able to discover and connect with people on goodreads
| 2.3.1 | From Gmail | User should be able to discover and connect with people from Gmail contacts
| 2.3.2 | Search on goodreads | User should be able to discover and connect with people using their goodreads accounts
3 |  | My Books
| 3.1 | Bookshelves | User should navigate to the page showing his entire list of books
| 3.1.1 | All books | User should be able to view his entire list of books
| 3.1.2 | Add shelf | User should be able to create a new list of books
| 3.2 | Your Reading Activity | User should be able to view his reading stats and activities
| 3.2.1 | Year in books | User should be able to view his reading stats from the previous years
| 3.2.2 | Reading Stats | User should be able to view his reading stats since his login period based on books, pages, publication year
4 |  | Browse
| 4.1 | Choice Awards 2019 | User should navigate to the page showing the award winning books of 2019
| 4.2 | New releases | User should navigate to the page showing the list newly released and to-be released books
| 4.3 | News and Interviews | User should navigate to the page showing articles and news about books and authors
| 4.3.1 | Articles | User should navigate to the page showing the entire list of articles about authors and books
| 4.3.2 | Interviews | User should navigate to the page showing interviews with various authors
5 |  | Community
| 5.1 | Groups | User should navigate to the page showing the list of popular groups on goodreads
| 5.1.1 | Search groups | User should be able to search for groups based on group names and/or description
| 5.2 | Quotes | User should be able to navigate to the page showing quotes by authors or excerpts from any books
| 5.3 | Quizes | User should be able to navigate to the page showing quizzes based on books or authors
| 5.4 | Ask the Author | User should navigate to the page showing popular questions asked to various authors and post questions

## Test Script
Scenario Id | Sub Scenario Id | Script ID/Step | Description | Expected Result
1 |  |  | Home Page
| 1.1 |  | Sign Up | User should get registered
|  | 1 | Enter username | Accepts valid username
|  | 2 | Enter email address | Accepts valid email address
|  | 3 | Enter password | Accepts valid password
|  | 4 | Click on 'Sign up' | Click operation should successfully register the user
| 1.2 |  | Sign In | User Should be allowed to Login
| 1.2.1 |  | Sign in with email address and password | User Should be allowed to login with email address and password
|  | 1 | Enter registered email ID | User should be allowed to enter valid email ID
|  | 2 | Enter user password | User should be allowed to enter a valid password
|  | 3 | Click on 'Sign in' | Click operation should successfully login the user
| 1.2.2 |  | Sign in using Facebook account | User should be allowed to login by logging into Facebook account
|  | 1 | Click on the Facebook button | Click operation should direct to a facebook login page
|  | 2 | Login with valid Facebook credentials | Successful login should redirect back to goodreads home page
| 1.2.3 |  | Sign in using Twitter account | User should be allowed to login by logging into Twitter account
|  | 1 | Click on the Twitter button | Click operation should direct to a Twitter login page
|  | 2 | Login with valid Twitter credentials | Successful login should redirect back to goodreads home page
| 1.2.4 |  | Sign in using Google account | User should be allowed to login by logging into Google account
|  | 1 | Click on the Google button | Click operation should direct to a Google login page
|  | 2 | Login with valid Amazon credentials | Successful login should redirect back to goodreads home page
| 1.2.5 |  | Sign in using Amazon account | User should be allowed to login by logging into Amazon account
|  | 1 | Click on the Amazon button | Click operation should direct to a Amazon login page
|  | 2 | Login with valid Amazon credentials | Successful login should redirect back to goodreads home page
2 |  |  | Home
| 2.1 |  | Currently Reading | User should be able to search for boks, get recommendations and post upates
| 2.1.1 |  | Search Books | User should be able to search for books and get suggestions as the name is typed
|  | 1 | Enter book or author name on 'Search Books' text field | Text operation should be validated and suggestions be given as the full name is being entered
|  | 2 | Click on the search logo or hit enter | User should navigate to the page showing all the books related to the search words
|  | 3 | Click on the desired book | Click operation should navigate to the books details page
|  | 4 | Click on 'Stores' | Click operation should show a drop down to select purchase options
|  | 5 | Click on a suitable store | Click operation should navigate to purchase page
| 2.1.2 |  | Recommendations | User should get suggestions on what books to read based on their reading taste
|  | 1 | Click on 'Recommendations' | Click operation should navigate to the page showing recommended books for the user
|  | 2 | Click on the desired book | Click operation should navigate to the books details page
|  | 3 | Click on 'Want to read' | Click operation should add the book to the reading wishlist
| 2.1.3 |  | General Update | User should be able to update their status on books and reading schedules
|  | 1 | Click on 'General update' | Click operation should display a text box with a limit of 420 characters
|  | 2 | Enter any thoughts to update goodread friends and click 'Save' | Click operation should save the user status update
| 2.2 |  | Reading Challenge | User should be able to set target number of books for the current year
| 2.2.1 |  | Set challenge | User should be able set the number of books he intend to finish reading during the current year
|  | 1 | Click on the text field below 'I want to read' | Click operation should activate the text field
|  | 2 | Click the incrementer/decrementer button to set the target number of books | Click operation should increase/decrease the number of books
|  | 3 | Click on 'Start Challenge' button | Click operation should set the challenge number
| 2.3 |  | Friends on goodreads | User should be able to discover and connect people on goodreads.com
| 2.3.1 |  | From Gmail | User should be able to discover and connect people from Gmail contacts
|  | 1 | Click on Friends icon | Click operation should naviagte to the 'Friends' page
|  | 2 | Click on 'Add some' | Click operation should navigate to 'Add Friends' page
|  | 3 | Click on the Gmail button | Click operation should navigate to the page showing the list of contacts
|  | 4 | Click on 'add friends' | Click operation should send an email invite to the selected contacts
| 2.3.2 |  | Search on goodreads | User should be able to discover and connect with people using their goodreads accounts
|  | 1 | Click on Friends icon | Click operation should naviagte to the 'Friends' page
|  | 2 | Click on 'Add some' | Click operation should navigate to 'Add Friends' page
|  | 3 | Click on 'Friends of friends' button | Click operation should navigate to the page showing the list of friends
|  | 4 | Click on the friend to add to your circle | Click operation should add the friend to your circles
3 |  |  | My Books
| 3.1 |  | Bookshelves | User should navigate to the page showing his entire list of books
|  | 3.1.1 | All books | User should be able to view his entire list of books
|  | 1 | Click on 'My Books' | Click operation should navigate to the 'My Books' page
|  | 2 | Click on 'All' | Click operation should display the list of books the user has read, saved to wishlist and currently reading arranged according to cover, title, author, avg rating, shelves and so on
|  | 3.1.2 | Add shelf | User should be able to create a new list of books
|  | 1 | Click on 'My Books' | Click operation should navigate to the 'My Books' page
|  | 2 | Click on 'Add shelf' button | Click operation should display a text box to enter the shelf name
|  | 3 | Enter a shelf name | Text operation should be validated
|  | 4 | Click 'add' | Click operation should add a new shelf
| 3.2 |  | Your Reading Activity | User should be able to view his reading stats and activities
| 3.2.1 |  | Year in books | User should be able to view his reading stats from the previous years
|  | 1 | Click on 'Year in Books' | Click operation should navigate to the page showing the reading activity for the past year
|  | 2 | Click on 'See previous year' | Click operation should navigate to the page showing the reading activity for the just previous year
| 3.2.2 |  | Reading Stats | User should be able to view his reading stats since his login period based on books, pages, publication year
|  | 1 | Click on 'Reading Stats' | Click operation should navigate to the page showing all the books read by the user
|  | 2 | Click on 'Publication year' radio button | Click operation sorts the list based on the publication year of the book
4 |  |  | Browse
| 4.1 |  | Choice Awards 2019 | User should navigate to the page showing the award winning books of 2019
|  | 1 | Click on 'Choice Awards' | Click operation should navigate to the goodreads Choice Awards 2019 page
|  | 2 | Click on the desired book | Click operation should navigate to the books details page
|  | 3 | Click on the drop-down button | Click operation shows the list of shelves available for the user
|  | 4 | Click on a desired shelf | Click operation adds the book to that shelf
| 4.2 |  | New releases | User should navigate to the page showing the list newly released and to-be released books
|  | 1 | Click on 'New releases' | Click operation should navigate to the page showing all the new releasing books
|  | 2 | Click on 'By genre' | Click operation should show the books categorised into genres
|  | 3 | Click on a desired book | Click operation should navigate to the page showing the details of the book
|  | 4 | Click on 'Amazon' button | Click operation navigates to the amazon.com page for the book
|  | 5 | Click on a desired book format and click 'Prebook' | Click operation should navigate to the payment page
| 4.3 |  | News and Interviews | User should navigate to the page showing articles and news about books and authors
|  | 1 | Click on News and Articles under 'Browse' | Click operation should navigate to the page showing articles and news about books and authors
| 4.3.1 |  | Articles | User should navigate to the page showing the entire list of articles about authors and books
|  | 1 | Click on 'Articles' | Click operation should navigate to the articles page showing news and particulars about various books
|  | 2 | Click on a desired article | Click operation navigates to the full article for the user to read
| 4.3.2 |  | Interviews | User should navigate to the page showing interviews with various authors
|  | 1 | Click on 'Interviews' | Click operation should navigate to the page showing interview reports with various authors
|  | 2 | Click on a desired article | Click operation navigates to the full article for the user to read
5 |  |  | Community
|  | 1 | Click on 'Community' | Click operation shows a drop-down menu to navigate to Groups, Discussions, Quotes, etc
| 5.1 |  | Groups | User should navigate to the page showing the list of popular groups on goodreads
|  | 1 | Click on the 'Groups' hyperlink | Click operation should navigate to the page showing popular groups on goodreads.com
| 5.1.1 |  | Search groups | User should be able to search for groups based on group names and/or description
|  | 1 | Enter a group name or description to search | Type operation should be validated
|  | 2 | Click on 'Search groups' | Click operation should show all groups matching the search words
|  | 3 | Click on a desired group | Click operation should navigate to the page showing the group details
|  | 4 | Click on 'Join group' | Click operation should make the user a member of the group
| 5.2 |  | Quotes | User should be able to navigate to the page showing quotes by authors or excerpts from any books
|  | 1 | Click on 'Quotes' hyperlink | Click operation on link should navigate to the Quotes page
|  | 2 | Type a keyword or author | Type operation should be validated
|  | 3 | Click on 'Search' button | Click operation should the list of quotes matching the search word
| 5.3 |  | Quizes | User should be able to navigate to the page showing quizzes based on books or authors
|  | 1 | Click on 'Quizzes' hyperlink | Click operation on link should navigate to the Quizzes page
|  | 2 | Click on a desired quiz to start taking the quiz | Click operation should navigate to the page starting the quiz
| 5.4 |  | Ask the Author | User should navigate to the page showing popular questions asked to various authors and post questions
|  | 1 | Click on 'Ask the Author' hyperlink | Click operation on link should navigate to the Ask the Author page
|  | 2 | Click on a desired featured author | Click operation should navigate to the page showing more about the author with an option to ask a question
|  | 3 | Type a question to the author | Type operation should be validated
|  | 4 | Click 'Ask' | Click operation posts the question to the author

## Test Script Execution
Scenario Id | Sub Scenario Id | Script ID/Step | Description | Expected Result | Actual | Conclusion
1 |  |  | Home Page
| 1.1 |  | Sign Up | User should get registered
|  | 1 | Enter username | Accepts valid username | Accepted Valid User name | PASS
|  | 2 | Enter email address | Accepts valid email address | Accepted Valid Email address | PASS
|  | 3 | Enter password | Accepts valid password | Accepted Valid Password | PASS
|  | 4 | Click on 'Sign up' | Click operation should successfully register the user | Successfully registered | PASS
| 1.2 |  | Sign In | User Should be allowed to Login
| 1.2.1 |  | Sign in with email address and password | User Should be allowed to login with email address and password
|  | 1 | Enter registered email ID | User should be allowed to enter valid email ID | Accepted valid Email Id | PASS
|  | 2 | Enter user password | User should be allowed to enter a valid password | Accepted Valid Password | PASS
|  | 3 | Click on 'Sign in' | Click operation should successfully login the user | Logged in successfully | PASS
| 1.2.2 |  | Sign in using Facebook account | User should be allowed to login by logging into Facebook account
|  | 1 | Click on the Facebook button | Click operation should direct to a facebook login page | Click operation didn't direct to any page | FAIL
|  | 2 | Login with valid Facebook credentials | Successful login should redirect back to goodreads home page | Couldn't log in to Facebook | FAIL
| 1.2.3 |  | Sign in using Twitter account | User should be allowed to login by logging into Twitter account
|  | 1 | Click on the Twitter button | Click operation should direct to a Twitter login page | Click operation directed to Twitter login | PASS
|  | 2 | Login with valid Twitter credentials | Successful login should redirect back to goodreads home page | Successfully redirected back to goodreads home page | PASS
| 1.2.4 |  | Sign in using Google account | User should be allowed to login by logging into Google account
|  | 1 | Click on the Google button | Click operation should direct to a Google login page | Click operation directed to Google login | PASS
|  | 2 | Login with valid Amazon credentials | Successful login should redirect back to goodreads home page | Successfully redirected back to goodreads home page | PASS
| 1.2.5 |  | Sign in using Amazon account | User should be allowed to login by logging into Amazon account
|  | 1 | Click on the Amazon button | Click operation should direct to a Amazon login page | Click operation directed to Amazon login | PASS
|  | 2 | Login with valid Amazon credentials | Successful login should redirect back to goodreads home page | Successfully redirected back to goodreads home page | PASS
2 |  |  | Home
| 2.1 |  | Currently Reading | User should be able to search for boks, get recommendations and post upates
| 2.1.1 |  | Search Books | User should be able to search for books and get suggestions as the name is typed
|  | 1 | Enter book or author name on 'Search Books' text field | Text operation should be validated and suggestions be given as the full name is being entered | Text operation validated but suggestions were not given | FAIL
|  | 2 | Click on the search logo or hit enter | User should navigate to the page showing all the books related to the search words | Navigated successfully to the search page | PASS
|  | 3 | Click on the desired book | Click operation should navigate to the books details page | Navigated successfully to the book details page | PASS
|  | 4 | Click on 'Stores' | Click operation should show a drop down to select purchase options | Successfully showed drop down menu with 6 purchase options | PASS
|  | 5 | Click on a suitable store | Click operation should navigate to purchase page | Successfully navigated to the purchase page | PASS
| 2.1.2 |  | Recommendations | User should get suggestions on what books to read based on their reading taste
|  | 1 | Click on 'Recommendations' | Click operation should navigate to the page showing recommended books for the user | Navigated successfully to the recommendations page | PASS
|  | 2 | Click on the desired book | Click operation should navigate to the books details page | Navigated successfully to the book details page | PASS
|  | 3 | Click on 'Want to read' | Click operation should add the book to the reading wishlist | Successfully added book to Wishlist | PASS
| 2.1.3 |  | General Update | User should be able to update their status on books and reading schedules
|  | 1 | Click on 'General update' | Click operation should display a text box with a limit of 420 characters | Text box displayed with 420 characters limit | PASS
|  | 2 | Enter any thoughts to update goodread friends and click 'Save' | Click operation should save the user status update | Status update was not saved | FAIL
| 2.2 |  | Click operation should navigate to the selected product details page | User should navigate to Women's Fashion Store Page
| 2.2.1 |  | Set challenge | User should be able set the number of books he intend to finish reading during the current year
|  | 1 | Click on the text field below 'I want to read' | Click operation should activate the text field | Text box displayed | PASS
|  | 2 | Click the incrementer/decrementer button to set the target number of books | Click operation should increase/decrease the number of books | Incrementer and decrementer was working | PASS
|  | 3 | Click on 'Start Challenge' button | Click operation should set the challenge number | Could not set the challenge target number of books | FAIL
| 2.3 |  | Friends on goodreads | User should be able to discover and connect people on goodreads.com
| 2.3.1 |  | From Gmail | User should be able to discover and connect people from Gmail contacts
|  | 1 | Click on Friends icon | Click operation should naviagte to the 'Friends' page | Navigated to 'Friends' page | PASS
|  | 2 | Click on 'Add some' | Click operation should navigate to 'Add Friends' page | Navigated to 'Add friends' page | PASS
|  | 3 | Click on the Gmail button | Click operation should navigate to the page showing the list of contacts | List of contacts was shown | PASS
|  | 4 | Click on 'add friends' | Click operation should send an email invite to the selected contacts | Email was sent to all selected contacts | PASS
| 2.3.2 |  | Search on goodreads | User should be able to discover and connect with people using their goodreads accounts
|  | 1 | Click on Friends icon | Click operation should naviagte to the 'Friends' page | Navigated to 'Friends' page | PASS
|  | 2 | Click on 'Add some' | Click operation should navigate to 'Add Friends' page | Navigated to 'Add friends' page | PASS
|  | 3 | Click on 'Friends of friends' hyperlink | Click operation should navigate to the page showing the list of friends | Navigated to list of friends | PASS
|  | 4 | Click on the friend to add to your circle | Click operation should add the friend to your circles | Friend added successfully | PASS
3 |  |  | My Books
| 3.1 |  | Bookshelves | User should navigate to the page showing his entire list of books
|  | 3.1.1 | All books | User should be able to view his entire list of books
|  | 1 | Click on 'My Books' | Click operation should navigate to the 'My Books' page | Navigated to 'My Books' page | PASS
|  | 2 | Click on 'All' | Click operation should display the list of books the user has read, saved to wishlist and currently reading arranged according to cover, title, author, avg rating, shelves and so on | Displayed the list of all books | PASS
|  | 3.1.2 | Add shelf | User should be able to create a new list of books
|  | 1 | Click on 'My Books' | Click operation should navigate to the 'My Books' page | Navigated to 'My Books' page | PASS
|  | 2 | Click on 'Add shelf' button | Click operation should display a text box to enter the shelf name | Text box displayed | PASS
|  | 3 | Enter a shelf name | Text operation should be validated | Text operation validated | PASS
|  | 4 | Click 'add' | Click operation should add a new shelf | Error message displayed, but shelf added | FAIL
| 3.2 |  | Your Reading Activity | User should be able to view his reading stats and activities
| 3.2.1 |  | Year in books | User should be able to view his reading stats from the previous years
|  | 1 | Click on 'Year in Books' | Click operation should navigate to the page showing the reading activity for the past year | Navigated to reading activity page | PASS
|  | 2 | Click on 'See previous year' | Click operation should navigate to the page showing the reading activity for the just previous year | Navigated to previous year's page | PASS
| 3.2.2 |  | Reading Stats | User should be able to view his reading stats since his login period based on books, pages, publication year
|  | 1 | Click on 'Reading Stats' | Click operation should navigate to the page showing all the books read by the user | Navigated to page showing all read books | PASS
|  | 2 | Click on 'Publication year' radio button | Click operation sorts the list based on the publication year of the book | Sorting by published year worked well | PASS
4 |  |  | Browse
| 4.1 |  | Choice Awards 2019 | User should navigate to the page showing the award winning books of 2019
|  | 1 | Click on 'Choice Awards' | Click operation should navigate to the goodreads Choice Awards 2019 page | Navigated to the goodreads Choice Awards 2019 page | PASS
|  | 2 | Click on the desired book | Click operation should navigate to the books details page | Navigated to the books details page | PASS
|  | 3 | Click on the drop-down button | Click operation shows the list of shelves available for the user | List of shelves shown correctly | PASS
|  | 4 | Click on a desired shelf | Click operation adds the book to that shelf | Click operation should navigate to the goodreads Choice Awards 2019 page | PASS
| 4.2 |  | New releases | User should navigate to the page showing the list newly released and to-be released books
|  | 1 | Click on 'New releases' | Click operation should navigate to the page showing all the new releasing books | Navigated to the 'New Releases' page | PASS
|  | 2 | Click on 'By genre' | Click operation should show the books categorised into genres | Successfully categorised into genres | PASS
|  | 3 | Click on a desired book | Click operation should navigate to the page showing the details of the book | Navigated to the books details page | PASS
|  | 4 | Click on 'Amazon' button | Click operation navigates to the amazon.com page for the book | Navigated to the amazon website | PASS
|  | 5 | Click on a desired book format and click 'Prebook' | Click operation should navigate to the payment page | Navigated to the payment page | PASS
| 4.3 |  | News and Interviews | User should navigate to the page showing articles and news about books and authors
|  | 1 | Click on News and Articles under 'Browse' | Click operation should navigate to the page showing articles and news about books and authors | Navigated to 'News and Articles' page | PASS
| 4.3.1 |  | Articles | User should navigate to the page showing the entire list of articles about authors and books
|  | 1 | Click on 'Articles' | Click operation should navigate to the articles page showing news and particulars about various books | Navigated to Articles page | PASS
|  | 2 | Click on a desired article | Click operation navigates to the full article for the user to read | Navigated to the full article | PASS
| 4.3.2 |  | Interviews | User should navigate to the page showing interviews with various authors
|  | 1 | Click on 'Interviews' | Click operation should navigate to the page showing interview reports with various authors | Navigated to Interviews page | PASS
|  | 2 | Click on a desired article | Click operation navigates to the full article for the user to read | Navigated to the full article | PASS
5 |  |  | Community
|  | 1 | Click on 'Community' | Click operation shows a drop-down menu to navigate to Groups, Discussions, Quotes, etc | Navigated to the Community page | PASS
| 5.1 |  | Groups | User should navigate to the page showing the list of popular groups on goodreads
|  | 1 | Click on the 'Groups' hyperlink | Click operation should navigate to the page showing popular groups on goodreads.com | Navigated to the 'Groups' page | PASS
| 5.1.1 |  | Search groups | User should be able to search for groups based on group names and/or description
|  | 1 | Enter a group name or description to search | Type operation should be validated | Type operation validated | PASS
|  | 2 | Click on 'Search groups' | Click operation should show all groups matching the search words | Search list was showed correctly | PASS
|  | 3 | Click on a desired group | Click operation should navigate to the page showing the group details | Navigated to the group details page | PASS
|  | 4 | Click on 'Join group' | Click operation should make the user a member of the group | User added to the group | PASS
| 5.2 |  | Quotes | User should be able to navigate to the page showing quotes by authors or excerpts from any books
|  | 1 | Click on 'Quotes' hyperlink | Click operation on link should navigate to the Quotes page | Navigated to the Quotes page | PASS
|  | 2 | Type a keyword or author | Type operation should be validated | Type operation validated | PASS
|  | 3 | Click on 'Search' button | Click operation should the list of quotes matching the search word | Search list was showed correctly | PASS
| 5.3 |  | Quizes | User should be able to navigate to the page showing quizzes based on books or authors
|  | 1 | Click on 'Quizzes' hyperlink | Click operation on link should navigate to the Quizzes page | Navigated to the 'Quizzes' page | PASS
|  | 2 | Click on a desired quiz to start taking the quiz | Click operation should navigate to the page starting the quiz | Quiz taken successfully | PASS
| 5.4 |  | Ask the Author | User should navigate to the page showing popular questions asked to various authors and post questions
|  | 1 | Click on 'Ask the Author' hyperlink | Click operation on link should navigate to the Ask the Author page | Navigated to the 'Ask the Author' page | PASS
|  | 2 | Click on a desired featured author | Click operation should navigate to the page showing more about the author with an option to ask a question | Navigated to the author's page | PASS
|  | 3 | Type a question to the author | Type operation should be validated | Type operation validated | PASS
|  | 4 | Click 'Ask' | Click operation posts the question to the author | Question posted successfully | PASS

## Defect
Scenario Id | Sub Scenario Id | Script ID/Step | Defect ID | Defect Description | Description | Expected Result | Severity
1 |  |  |  |  | Authentication
| 1.2.2 |  |  |  | User Login | User should be logged in
|  | 1 |  |  | Click on Facebook button | Option to login to Facebook
|  |  | #D1010 | Unable to direct to Facebook login page | On clicking Facebook button no action is done | Click operation should direct to a Facebook login page | SHOW STOPPER
|  | 2 |  |  | Login to Facebook and redirect to goodreads.com | Login to Facebook
|  |  | #D1015 | Unable to login to goodreads.com | Login cannot be done | Redirect back to goodreads.com | SHOW STOPPER
2 |  |  |  |  | Home
| 2.1.1 |  |  |  | Currently reading | User should be able to search for boks, get recommendations and post upates
|  | 1 |  |  | Search books | User should be able to search for books and get suggestions as the name is typed
|  |  | #D5445 | Failed to show suggestions as the names were typed | Text operation validated but no suggestions were shown | Text operation should be validated and suggestions be given as the full name is being entered | LOW
| 2.1.3 |  |  |  | Currently reading | User should be able to search for boks, get recommendations and post upates
|  | 2 |  |  | General Update | User should be able to update their status on books and reading schedules
|  |  | #D5432 | Failed to save general update | Status update was not saved | Click operation should save the user status update | MEDIUM
| 2.2.1 |  |  |  | Reading Challenge | User should be able to set target number of books for the current year
|  | 3 |  |  | Set Challenge | User should be able set the number of books he intend to finish reading during the current year
|  |  | #D5478 | Failed to set the challenge number of books | Could not set the challenge target number of books | Click operation should save the user status update | HIGH
3 |  |  |  |  | My Books
| 3.1.2 |  |  |  | Bookshelves | User should navigate to the page showing his entire list of books
|  | 4 |  |  | Add shelf | User should be able to create a new list of books
|  |  | #D5467 | Wrong error message being shown | Error message saying list not created shown, but shelf was created | Click operation should add a new shelf | LOW